## Task Checklist
Task ID | Task | Item # | Requirement (what to do) | How to Verify (what done looks like) | Done | Date Completed | Evidence / Link
1.1 | Development Environment Setup | 1 | Install Node.js LTS | `node -v` prints v20 or higher | Yes | 2026-08-27
1.1 | Development Environment Setup | 2 | Confirm npm works | `npm -v` prints a version number | Yes | 2026-08-27
1.1 | Development Environment Setup | 3 | Install TypeScript + create tsconfig.json | `npx tsc --noEmit` runs without config errors | Yes | 2026-08-27
1.1 | Development Environment Setup | 4 | Configure Git (name + email) | `git config user.name` returns your name | Yes | 2026-08-28
1.1 | Development Environment Setup | 5 | Create GitHub repository | Repo URL opens in a browser | Yes | 2026-08-28
1.1 | Development Environment Setup | 6 | Write README with project description | README renders on the repo homepage | Yes | 2026-08-28
1.1 | Development Environment Setup | 7 | Configure ESLint | `npx eslint .` runs without config errors | Yes | 2026-08-28
1.1 | Development Environment Setup | 8 | Configure Prettier + format-on-save | Saving a messy file auto-formats it | No
1.1 | Development Environment Setup | 9 | Install Postman + create first collection | Collection with at least 1 saved request | Yes | 2026-08-28
1.1 | Development Environment Setup | 10 | Install VS Code extensions (ESLint, Prettier, GitLens) | All three show as enabled | Yes | 2026-08-28
1.2 | Git Workflow | 1 | Clone the repository locally | `git status` works inside the folder | Yes | 2026-08-29
1.2 | Git Workflow | 2 | Create a feature branch | `git branch` shows feature/<name> | Yes | 2026-08-29
1.2 | Git Workflow | 3 | Make 5+ atomic commits with clear messages | `git log --oneline` reads like a changelog | No
1.2 | Git Workflow | 4 | Push branch to remote | Branch is visible on GitHub | No
1.2 | Git Workflow | 5 | Open a PR with a written description | PR page shows summary of the change | No
1.2 | Git Workflow | 6 | Merge the PR after self-review | main branch contains your commits | No
1.2 | Git Workflow | 7 | Create and resolve a merge conflict | Conflict resolved with no code lost | No
2.1 | TypeScript Fundamentals | 1 | Create Student class with constructor | `new Student(...)` creates valid instances | No
2.1 | TypeScript Fundamentals | 2 | Define interfaces for all data models | No `any` types in model code | No
2.1 | TypeScript Fundamentals | 3 | Use enums or union types for fixed values | Status/type fields reject invalid values | No
2.1 | TypeScript Fundamentals | 4 | Use a generic (e.g. Repository<T>) | Same code reused for two different types | No
2.1 | TypeScript Fundamentals | 5 | Implement async/await with a simulated API | Async calls resolve and errors are caught | No
2.1 | TypeScript Fundamentals | 6 | Add input validation with clear error messages | Bad input prints a helpful message, no crash | No
2.1 | TypeScript Fundamentals | 7 | Build CLI menu: add/list/update/delete students | All 4 operations work from the terminal | No
2.1 | TypeScript Fundamentals | 8 | Compile clean in strict mode | `tsc` with strict:true gives zero errors | No
3.1 | REST API | 1 | Scaffold the project (Express/Nest) | Server starts and logs the port | No
3.1 | REST API | 2 | POST /students creates a student | Returns 201 with the created body | No
3.1 | REST API | 3 | GET /students and GET /students/:id work | 200 with data; 404 for a missing id | No
3.1 | REST API | 4 | PUT/PATCH updates a student | Returns 200 with the updated body | No
3.1 | REST API | 5 | DELETE removes a student | Returns 204; following GET returns 404 | No
3.1 | REST API | 6 | Add request validation (zod/joi/DTO) | Invalid body returns 400 with a clear message | No
3.1 | REST API | 7 | Add centralized error handler | Errors return clean JSON, never a stack trace | No
3.1 | REST API | 8 | Add request logging middleware | Each request logs method, path, status | No
4.1 | Database Design | 1 | Draw the ERD | Diagram saved in /docs and matches requirements | No
4.1 | Database Design | 2 | Create tables with PK/FK relationships | Foreign keys enforce valid references | No
4.1 | Database Design | 3 | Apply constraints (NOT NULL, UNIQUE) | Inserting bad data fails at the DB level | No
4.1 | Database Design | 4 | Set up migrations | Migrate up and down both work | No
4.1 | Database Design | 5 | Write a seed script | One command fills the DB with sample data | No
4.1 | Database Design | 6 | Connect API to the DB (no in-memory) | Data survives an app restart | No
5.1 | Authentication | 1 | Build register endpoint with validation | Duplicate email is rejected with clear error | No
5.1 | Authentication | 2 | Hash passwords with bcrypt | DB shows hashes, never plain text | No
5.1 | Authentication | 3 | Login returns a JWT | Token decodes with the expected payload | No
5.1 | Authentication | 4 | Protect routes with auth middleware | Request without token returns 401 | No
5.1 | Authentication | 5 | Add role/ownership check on one route | Wrong user gets 403 | No
5.1 | Authentication | 6 | Handle token expiry | Expired token returns 401, not a crash | No
5.1 | Authentication | 7 | Save auth flows in Postman | Collection covers register/login/protected | No
6.1 | Service Architecture | 1 | Controllers handle HTTP only | No business logic inside controllers | No
6.1 | Service Architecture | 2 | Move business logic into services | Services have no req/res objects | No
6.1 | Service Architecture | 3 | Repositories handle all data access | No SQL/ORM calls outside repositories | No
6.1 | Service Architecture | 4 | Define DTOs/types between layers | Layer boundaries use typed objects | No
6.1 | Service Architecture | 5 | Keep dependency flow one-directional | No circular imports | No
6.1 | Service Architecture | 6 | Document folder structure in README | A new dev can find where code belongs | No
7.1 | AI Chatbot | 1 | Configure LLM API key via environment variable | Key is not in Git history | No
7.1 | AI Chatbot | 2 | Build POST /chat endpoint calling the LLM | Sending a message returns an AI reply | No
7.1 | AI Chatbot | 3 | Store conversations in the DB | Messages visible in the conversations table | No
7.1 | AI Chatbot | 4 | Wire chat flow end to end (UI or Postman) | Multi-turn conversation works | No
7.1 | AI Chatbot | 5 | Handle loading state | User sees a pending indicator, not a freeze | No
7.1 | AI Chatbot | 6 | Handle AI/API failures gracefully | Outage shows a friendly error message | No
7.1 | AI Chatbot | 7 | Add a basic usage guard / rate limit | Spam requests get blocked politely | No
7.2 | Prompt Engineering | 1 | Write a system prompt for the study assistant | Bot stays in its study-helper role | No
7.2 | Prompt Engineering | 2 | Document constraints (scope, tone, refusals) | Off-topic requests are politely refused | No
7.2 | Prompt Engineering | 3 | Log 3+ prompt iterations with results | Doc shows measurable answer improvement | No
7.2 | Prompt Engineering | 4 | Test few-shot examples | Adding examples visibly improves format | No
7.2 | Prompt Engineering | 5 | Store final prompt in config, not scattered strings | One place to edit the prompt | No
7.3 | Conversation Memory | 1 | Persist messages per conversation | Reload shows full history | No
7.3 | Conversation Memory | 2 | Inject history window into the prompt | Bot answers follow-up questions correctly | No
7.3 | Conversation Memory | 3 | Truncate/summarize old messages | Long chats stay under the token limit | No
7.3 | Conversation Memory | 4 | Store and use user preferences | Bot remembers e.g. preferred language | No
7.3 | Conversation Memory | 5 | Survive an app restart | Restart, ask a follow-up — context still works | No
7.4 | Document Chat (RAG) | 1 | Build file upload endpoint (PDF) | Upload succeeds and file is stored | No
7.4 | Document Chat (RAG) | 2 | Extract text from PDFs | Extracted text matches the document | No
7.4 | Document Chat (RAG) | 3 | Implement + document a chunking strategy | /docs explains chunk size and overlap choice | No
7.4 | Document Chat (RAG) | 4 | Generate and store embeddings | Vectors stored per chunk | No
7.4 | Document Chat (RAG) | 5 | Similarity search returns relevant chunks | Test question retrieves the right passage | No
7.4 | Document Chat (RAG) | 6 | Cite sources in answers | Answer names page/section it came from | No
7.4 | Document Chat (RAG) | 7 | Handle questions with no relevant content | Bot says it does not know, no invention | No
7.4 | Document Chat (RAG) | 8 | Test with 3+ different PDFs | All three produce grounded answers | No
7.5 | Voice Assistant | 1 | Accept audio recording/upload | Audio file reaches the server | No
7.5 | Voice Assistant | 2 | Integrate speech-to-text | Clear speech transcribes accurately | No
7.5 | Voice Assistant | 3 | Route transcript through the chatbot pipeline | Spoken question gets an AI answer | No
7.5 | Voice Assistant | 4 | Return text-to-speech audio reply | Answer plays back as audio | No
7.5 | Voice Assistant | 5 | Record a full voice round-trip demo | Video/screen recording saved in /docs | No
8.1 | Socket.IO | 1 | Establish socket connection from client | Connect event logs on the server | No
8.1 | Socket.IO | 2 | Implement typing indicator | Second window shows 'typing…' live | No
8.1 | Socket.IO | 3 | Implement online presence list | List updates on connect/disconnect | No
8.1 | Socket.IO | 4 | Push a realtime notification on an event | Notification appears without refresh | No
8.1 | Socket.IO | 5 | Handle reconnection | Kill server, restart — client reconnects | No
9.1 | Optimization | 1 | Connect Redis | Redis ping succeeds from the app | No
9.1 | Optimization | 2 | Cache at least one hot endpoint | Second call visibly faster (log timings) | No
9.1 | Optimization | 3 | Invalidate cache on data change | Update shows fresh data, not stale cache | No
9.1 | Optimization | 4 | Add pagination to list endpoints | page/limit params return correct slices | No
9.1 | Optimization | 5 | Identify and optimize one slow query | Before/after timings recorded in /docs | No
10.1 | Testing | 1 | Set up test framework (Jest/Vitest) | `npm test` runs | No
10.1 | Testing | 2 | Write 5+ unit tests for services | All pass, cover core logic | No
10.1 | Testing | 3 | Write integration tests with a test DB | Tests use isolated test database | No
10.1 | Testing | 4 | Write API tests for main endpoints | CRUD + auth paths covered | No
10.1 | Testing | 5 | Test edge and error cases | Invalid input paths are asserted | No
10.1 | Testing | 6 | Generate a coverage report | 60%+ coverage on services | No
11.1 | Deployment | 1 | Write a Dockerfile | `docker build` succeeds | No
11.1 | Deployment | 2 | Create docker-compose for app + DB | `docker compose up` starts everything | No
11.1 | Deployment | 3 | Manage env vars properly | .env gitignored; .env.example committed | No
11.1 | Deployment | 4 | Add a health endpoint | /health returns status + uptime | No
11.1 | Deployment | 5 | Deploy (or run from a clean clone) | Fresh machine needs max 3 commands | No
11.1 | Deployment | 6 | Document deployment steps | /docs/deploy.md is complete | No
12.1 | Requirements Engineering | 1 | Write 8+ user stories | As a… I want… so that…' format | No
12.1 | Requirements Engineering | 2 | Define acceptance criteria per story | Each story is testable | No
12.1 | Requirements Engineering | 3 | Document assumptions and out-of-scope | Scope boundaries are explicit | No
12.1 | Requirements Engineering | 4 | Map stories to tasks/weeks | Each story points at a roadmap task | No
12.2 | API Design | 1 | Design all endpoints before coding | Endpoint list reviewed against stories | No
12.2 | API Design | 2 | Define status codes per endpoint | Success + error codes specified | No
12.2 | API Design | 3 | Specify the error response format | One consistent JSON error shape | No
12.2 | API Design | 4 | Write the OpenAPI/Swagger spec | Spec validates without errors | No
12.2 | API Design | 5 | Serve Swagger UI from the app | /docs endpoint shows try-it-out UI | No
12.3 | Code Review | 1 | Review an assigned/peer pull request | Comments posted on specific lines | No
12.3 | Code Review | 2 | Comment on naming and readability | At least 3 concrete suggestions | No
12.3 | Code Review | 3 | Find one security and one performance issue | Both documented with fixes | No
12.3 | Code Review | 4 | Submit a written review report | Report saved in /docs/reviews | No
12.4 | Debugging | 1 | Reproduce the bug with written steps | Steps reliably trigger the bug | No
12.4 | Debugging | 2 | Identify the root cause | Explanation covers cause, not symptom | No
12.4 | Debugging | 3 | Implement the fix | Bug no longer reproduces | No
12.4 | Debugging | 4 | Add a regression test | Test fails on old code, passes on new | No
12.5 | Documentation | 1 | Complete the README (setup/run/test) | A stranger can run the app from it | No
12.5 | Documentation | 2 | Write an architecture doc with diagram | Layers and data flow are drawn | No
12.5 | Documentation | 3 | Publish API documentation | Matches the live endpoints | No
12.5 | Documentation | 4 | Document AI prompts and design decisions | /docs explains the why, not just what | No
12.6 | Presentation | 1 | Prepare a demo script | Dry run fits in 15 minutes | No
12.6 | Presentation | 2 | Deliver the 15-minute demo | Live demo, no slides-only | No
12.6 | Presentation | 3 | Answer questions without AI assistance | Explains own code confidently | No
12.6 | Presentation | 4 | Write a reflection | 1 page: what I'd do differently | No
12.7 | AI Research | 1 | Select the weekly topic from Weekly Plan | Topic matches the assigned week | No
12.7 | AI Research | 2 | Write a 1-page summary in your own words | No copy-paste; sources listed | No
12.7 | AI Research | 3 | Present 10 minutes to the team | Peers can ask questions | No
12.7 | AI Research | 4 | Store summaries in /docs/research | One file per week, named by topic | No
13.1 | AI Campus Assistant (Capstone) | 1 | Write capstone requirements & scope doc | Approved at Week 15 checkpoint | No
13.1 | AI Campus Assistant (Capstone) | 2 | Complete auth module | Register/login/protected routes work | No
13.1 | AI Campus Assistant (Capstone) | 3 | Complete student data CRUD | All operations persist to DB | No
13.1 | AI Campus Assistant (Capstone) | 4 | Integrate the AI chatbot | Multi-turn chat with memory works | No
13.1 | AI Campus Assistant (Capstone) | 5 | Integrate RAG document chat | PDF Q&A with citations works | No
13.1 | AI Campus Assistant (Capstone) | 6 | Integrate the voice assistant | Voice round-trip works | No
13.1 | AI Campus Assistant (Capstone) | 7 | Integrate realtime notifications | Live updates without refresh | No
13.1 | AI Campus Assistant (Capstone) | 8 | Get the full test suite passing | `npm test` green, coverage reported | No
13.1 | AI Campus Assistant (Capstone) | 9 | Dockerize and deploy | `docker compose up` runs the full app | No
13.1 | AI Campus Assistant (Capstone) | 10 | Deliver final presentation + handover docs | Demo done; docs complete | No

## Evaluation Rubric
Category | Weight (%) | Mentor Score (1-5) | Weighted Points
Functionality | 40 |  | 0
Code Quality | 15 |  | 0
Architecture | 10 |  | 0
Database Design | 10 |  | 0
Documentation | 10 |  | 0
Git Usage | 5 |  | 0
Testing | 5 |  | 0
Communication & Explanation | 5 |  | 0
Total | 100 |  | 0
Pass Threshold (points) | 70
Overall Score (out of 100) | 0
Avg Task Mentor Score (Roadmap) | Not scored yet
Recommendation | Pending — score all categories